## Slide 1: Highway 5 at MSP Airport Richfield City Council
January 28, 2020

## Slide 2: Project Scope
Concrete overlay or reconstruction
Concrete pavement repair
Bridge Repair/Redeck
Will last 25 + years until next fix (minor CPR)
Will last 15 + years until next fix (bituminous overlay)
Concrete overlay or reconstruction
Concrete pavement repair
Bridge re-deck
Bridge repair
Notes: Airport to East
Original underlying concrete constructed in 1960
Jointed Reinforced Concrete
First asphalt Overlay in 1974
Resurfacing Projects in 1981, 1989, 1998, 2010
Pavement is old & tired, needs a long-term fix
Airport to West
Original concrete constructed in 1986
Jointed Reinforced Concrete
Minor Concrete Rehab in 2012
Another Concrete Rehab is needed

## Slide 3: Project Schedule
Project to be completed in one construction season
April
May
June
July
August
September
October
Stage 1
Stage 2
Stage 3
2020

## Slide 4: Project staging and detours
Stage 1
April to July 2020
EB Highway 5 Closed
Stage 1 and 2 are the stages we are most interested in and concerned about people getting to the airport
2020
A
M
J
J
A
S
O
2
3
1
Notes: Highway 5 closed 494 over Mississippi River

## Slide 5: Project staging and detours
Stage 1
April to July 2020
EB Highway 5 Closed
Detour routes

## Slide 6: Project staging and detours
Stage 2
July to August 2020
EB Highway 5 Closed
Partial closure of Hwy 5 and Hwy 62 interchange
2020
A
M
J
J
A
S
O
3
1
2
Notes: The closure of EB 5 scaled back to highway 62
One lane in each direction over river as traffic is moved to EB side
WB side of interchange closed
Hoping to have EB 5 open by stage 2, but unsure at this time

## Slide 7: Project staging and detours
Stage 3
August to October 2020
WB Highway 5 Closed
2020
A
M
J
J
A
S
O
2
3
1

## Slide 8: Project staging and detours
Stage 3
August to October 2020
EB Highway 5 Closed
Detour routes

## Slide 9: How will traffic be impacted?
How will traffic patterns change and what will be the impact?
Origin and destination data
Existing traffic data
Traffic modeling
These tools help us understand traffic issues and identify “problem spots”
Identify mitigation strategies to implement
Communicate impacts to the public
Identify areas to watch and have contingencies

## Slide 10: Communications
Real time travel info
Know before you go
Informed travel decision
Strategic Communications Group
Communication Consultant
MnDOT
Partners

## Slide 11: Know before you go
GOALS
Reach as many people as possible within a six-hour radius of the MSP Airport.
Communicate early and often so people are aware of construction well before they travel.
Keep people informed of detours and delays so they can understand the impacts to their trip and plan accordingly.
Create easy-to-use tools to help people prepare for what they may encounter while on the road.

## Slide 12: Know before you go
IMPLEMENTATION
Promotional website
Email updates
Airline information
Partner communications
Business communications
Paid advertising
Media coverage
Social media
Highway signage
Neighborhood outreach/ presentations

## Slide 13: Key audiences
KEY AUDIENCES
Local governments
Air travelers
Airport employees and functions (including EMS)
Visitors (travel agencies, hotels, chambers of commerce, convention & visitors bureaus)
Large employers
Area businesses
Commuters
Transit riders
Nearby neighborhoods
Destinations

## Slide 14: Promotional website
Interactive
Travel information and tools
  Current and upcoming traffic impacts
Planning information and tools for
  Air travelers
  Visitors
  Commuters
  Nearby neighborhoods
  Area businesses
Connections
  Project email updates
  Shareables (e.g. social media)
Partnerships and resources
Memorable URL
Easy navigation
WHAT’S DIFFERENT?

## Slide 15: Key dates (tentative)
Information coordination/preparedness
Jan - Apr
Mid/late Feb
Mid March
April
Mid April
Website (soft launch)
MnDOT construction kickoff
CONSTRUCTION BEGINS
Traffic impacts begin